## Project Information
#VALUE! | Project Charter
Project Information
Prooject Title | RHHJ Information System
Objective | The primary objective is to identify and deploy an information system for Rays of Hope Hospice Jinja (RHHJ) that can be used by the staff to manage patients receiving care
Scope | The scope of the project is to have a system that
Project Schedule
Kick-off meeting date | 2025-02-10
Expected start date | 2025-02-13
Expected completion date
Key Personnel
Sponsor | Sylvia
Program oversight | Margrethe Juncker
Implementation Team | Mbabazi Joanita, Namugambe Josephine, Walusansa Susan, Naleba Irene, Debbie Swanepoel, Mukiibi Henry
Project Manager | John Mwayi
Assistant Project Manager | Reshma Kakkar
Technical Advisor | Gene Ussery
Implementation Lead | Selam Emiru
Program Advisor remote | Peter Solberg

## Deliverables
#VALUE! | Deliverables
1 | Project Charter
2 | Project Management Plan
3 | Technical Working Group Members and Terms of Reference
3 | Requirements analysis
4 | Process Flow diagrams
5 | Evaluation scorecard
6 | SWOT analysis of systems under consideration

## Schedule
#VALUE! | Project Schedule
Milestone | Description | Start | Finish
Finalize Technical Working Group |  | 2025-02-10 | 2025-02-14
Complete and document Functional |  | 2025-03-10 | 2025-03-31
Evaluation Criteria |  | 2025-03-10 | 2025-03-14

## Risks
#VALUE! | Project Risks
Risk | Mitigation | Remarks
Hosting requirements by GoU | Work with Paul Mbaka to get a detailed understanding of what is permissible and ensure solutions are in compliance
Project management team's time constraints | weekly check in meetings with project manager to plan week schedule and task assignment
Managing Expectations of RHHJ staff | Regular communication and periodic review of scope of work